## Introduction
Matter 5: Site Allocations Methodology
Appendix 1
This Appendix consists of the following tabs:
NPPF Deliverable para A | NPPF para A definition states 'all sites with detailed planning permission, should be considered deliverable until permission expires, unless there is clear evidence that homes will not be delivered within five years'.
This tab sets out delivery evidence for Local Plan site allocations with full planning permission (at the time of submission of the Local Plan), which the trajectory expects to be delivered in years 1-5.
NPPF deliverable para B | NPPF para B definition states 'where a site has outline planning permission for major development, has been allocated in a development plan... it should only be considered deliverable where there is clear evidence that housing completions will begin on site within five years'.
This tab sets out delivery evidence for Local Plan allocations with outline permission, or a Local Plan allocation, (at the time of submission of the Local Plan) which the trajectory expects to be delivered in years 1-5.
NPPF Developable | NPPF developable definition states 'sites should be in a suitable location for housing development with a reasonable prospect that they will be available and could be viably developed at the point envisaged'.
This tab sets out delivery evidence for Local Plan site allocations which are expected to be delivered after years 1-5.
NB site BW1 The Vineyard / Tangier Lane is not listed separately in the trajectory/tabs as housing development was completed in 2023-2024 (included in 'Completions')
It should be noted that all of this information is include in Appendix A of the Council's hearings statement for Matter 4: Meeting Housing Need

## NPPF Deliverable para A
Matter 5: Site Allocations Methodology
Sites in years 1-5 from Plan adoption - NPPF 'Deliverable' paragraph A (trajectory category D)
Local Plan Site Allocation Reference | Site Name | Dwelling Nos. | Planning Status as at 31st March 2025 | Delivery Information
Winchester Town
South Hampshire Urban Area
Market Towns and Rural Area
NA1 | The Dean, New Alresford | 20 | Allocated carried forward site NA2. Full planning permission 17/02306/FUL, 24/02009/FUL. | Full consent for 20 units not started, application for variation of condition under consideration. Part of allocated area remaining to gain consent (at April 2024) included at paragraph B tab (14 dwellings).
NA2 | Sun Lane, New Alresford | 302 | Allocated carried forward site NA3. Full planning permission - 21/01731/REM (302) | Full consent for 302 units (Taylor Wimpey), under construction. First dwellings (Alresford Down) are being marketed by Charters Estate Agents as available for occupation summer 2025.
SW1 | Land at The Lakes, Swanmore | 83 | Allocated carried forward site SW1. Full planning permission on two parts of the site - 19/02421/FUL & 21/03119/FUL (64 + 19 = 83). | Land off New Rd 19/02421/FUL Granted15/03/22 - 64 units (Persimmon Homes) under construction. Belmont Farm 21/03119/FUL - Granted 30.01.24 - 19 units, not yet started, work progressing on discharge of pre-commencement conditions. Part of allocated area remaining to gain consent included at paragraph B tab (17 dwellings).
WK1 | East of Winchester Road, Wickham | 17 | Allocated carried forward site WK2. Full planning permission - 17/02615/FUL (120) | Remaining 17 homes from permission 17/02615/FUL for 120 dwellings (Bewley Homes). Under construction, largely complete, anticipated final 17 homes will be delivered 2024/2025.
WC1 | Morgans Yard, Waltham Chase | 80 | Allocated carried forward site WC1. Full planning permission - 21/02439/FUL issued 3/12/24 (80). Brownfield site | Full planning permission for 80 units granted 2024. Application to discharge pre-commencement conditions received December 2024. Occupiers vacating site / site clearance underway (see also Council statement on Matter 8).

## NPPF Deliverable para B
Matter 5: Site Allocations Methodology
Sites in years 1-5 from Plan adoption - NPPF 'Deliverable' paragraph B (trajectory categories E and H [part] )
Local Plan Site Allocation Reference | Site Name | Dwelling Nos. | Planning Status as at 31st March 2025 | Delivery Information
Winchester Town
W1 | Barton Farm Major Development Area | 1408 remaining | Allocated carried forward site WT2. Permissions granted: 09/02412/OUT, 13/02257/REM, 19/01983/REM, 19/02115/REM, 19/01616/REM, 19/02121/REM, 19/02124/REM | Phases 1a and 1b complete and occupied. Phase 2a under construction and partly occupied (264 homes). Phase 2b under construction (291 homes). Phase 3a under construction (208 homes). Phase 3b reserved matters recently submitted. Pre-app discussions with LPA on Phase 4 due to commence. The trajectory expects 555 dwellings in years 1-5 (95-115 per annum). (see also Council response to Matter 6).
W2 | Sir John Moore Barracks | 900 | Proposed allocation W2. Concept Masterplan agreed by WCC Cabinet on 12 Feb 2025 | A Planning Performance Agreement with the LPA was signed in 2024 and a Concept Masterplan was agreed by Cabinet 12/02/25. Outline planning application to be submitted Autumn 2025. The trajectory only expects 90 dwellings in years 1-5 (2028/29 & 2029/30) (see also Council response to Matter 6). | Sir John Moore Barracks Concept Masterplan | Avison Young on behalf of Defence Infrastructure Organisation
W7 | Central Winchester Regeneration area | 300 | Brownfield site. Allocated carried forward site WIN4. SPD adopted 20/06/2018. Permission 06/01901/FUL lapsed. | Development Delivery Plan approved by WCC Cabinet on 13 March 2025 (CAB3484 refers) – includes a timetable for planning permission (by end 2027), Phase A procurement and construction (early 2027 - mid 2030), Phase B procurement and construction (start 2029 - early 2034). The trajectory only expects 50 dwellings in years 1-5 (2029/30) (see also Council response to Matter 6).
W8 | Station Approach area | 250 | Allocated carried forward site WIN5. | Public consultation on the Concept Masterplan closed 27 October 2024, results are being analysed, with the intention to report the Concept Masterplan to Cabinet in June 2025 for endorsement. Trajectory only expects 35 dwellings in years 1-5 (2029/30) (see also Council response to Matter 6). | Station Approach - Winchester City Council
W9 | Bar End Depot | 30 | Brownfield site. Proposed allocation W9. | WCC Cabinet agreed the disposal of the site 15 October 2024 to McCarthy and Stone. Pre-application advice is due to be sought in the next few months and planning application expected in late 2025. Trajectory expects completion in years 1-5 (2027/28) (see also Council response to Matter 6). | CAB3447 Bar End Depot Disposal.pdf
South Hampshire Urban Area
SH1 | Newlands (West of Waterlooville) | 1129 remaining of original allocation | Allocated carried forward site SH2. Permission 21/02892/REM, 22/01031/REM, 21/02890/REM, 17/02957/REM, 10/02862/OUT, 18/02355/REM, 14/02872/REM, 16/02621/REM, 17/02956/REM, 14/00068/REM, 18/01351/REM, 17/01772/REM, 22/01877/REM | Grainger Site Delivery Statement shows various phases complete and others sold by Grainger and/or under construction (Phases 9C/11A - 10B/11B, 8, 12). Grainger expect to deliver future phases as follows: Phase 4 delivery expected 2034 Phase 5B delivery expected 2030 Phase 6 (Local Centre various parts) delivery expected 2027-2031 Phase 7 delivery expected 2028 Phase 13C delivery expected 2029. The trajectory expects 600 dwelling completions in years 1-5 (120 per annum). Grainger Delivery Statement expects 667 completions on Phases already sold to developers, with first occupations on other Phases by 2030 totalling a further 561 dwellings. |  | Bryony-Stala-obo-West-Waterlooville_Grainger-NON-AQTS-3B5G-A-Supporting-Document_Redacted.pdf
SH2 | North Whiteley | 2076 | Allocated carried forward site SH3. Permission 15/00485/OUT. Numerous reserved matters approvals covering most phases. | Development commenced, many phases have reserved matters permitted and are under construction or completed - see link to North Whiteley web page ('Latest status'). This shows that all phases have full planning consent (3,318 dwellings out of 3,500), with only phases 35 and 36 remaining to submit reserve matters applications (182 dwellings). This is expected in 2025 with delivery in 2027-2028. Trajectory expects 1425 dwellings completions in years 1-5 (225-350 per annum). With only 182 dwellings remaining on phases that do not currently have reserved matters consent, there are considerably more dwellings than this which are 'deliverable' (with full consent). |  | https://www.winchester.gov.uk/planning/major-development-projects/north-whiteley
SH3 | Whiteley Green | 30 | Brownfield site. Allocated carried forward site SHUA1 | Site owned by Hampshire County Council, part to be retained for special educational needs development (capacity for 30 dwellings remaining). HCC produced a (confidential) development brief in January 2025 to be published when the site is marketed. HCC suggest this will not be immediately and the trajectory has been updated to show expected completion in 2028/29-2029/30. HCC made representations on the Regulation 19 Local Plan supporting the allocation and suggesting amendments to update the position.
Market Towns and Rural Area
NA1 | The Dean, New Alresford | 14 | Allocated carried forward site NA2. Full planning permission 23/00701/FUL. | Full consent for 14 remaining units now granted (after 1 April 2024) and under construction (Metis Homes).
KW1 | Cornerways & Merrydale | 45 | Proposed allocation. Brownfield site | Site owned by Hampshire County Council. HCC confirmed in November 2024 plans for a 80-100 bed nursing home (44-56 dwelling equivalents). The November 2024 report and discussions with HCC indicate that the site will not be fully operational until at least late 2027. As this is now likely to be a care development the trajectory has been updated to reflect HCC's programme, with completion expected in years 2028/29-2029/30 (see also Council response to Matter 8).
SW1 | Land at The Lakes, Swanmore | 17 | Allocated carried forward site SW1. Remaining part of Local Plan allocation with estimated capacity of 17 dwellings. | Remaining part of Local Plan allocation for 100 units (see paragraph A tab for other parts). Request for pre-application advice received in August 2024 (20 units, reduced to 18), estimated capacity 17 dwellings (see also Council response to Matter 8).
KN1 | Ravenswood | 200 | Planning application 18/01612/OUT agreed subject to signing of s106. Not yet determined. | Resolution to grant consent subject to completion of S106 obligation. Site owned by Homes England which is progressing the S106 obligation. Homes England made representations on the Regulation 19 Local Plan supporting the allocation and suggesting amendments to update the position (see also Council response to Matter 8). | ANON-AQTS-32TD-P

## NPPF Developable
Matter 5: Site Allocations Methodology
Sites in years 6-15 from Plan adoption - NPPF 'Developable' (trajectory category H [part] )
Local Plan Site Allocation Reference | Site Name | Dwelling Nos. | Planning Status as at 31st March 2025 | Delivery Information
Winchester Town
W3 | St Peters Car Park | 30 | Proposed allocation W3 | WCC Property Board have agreed to the disposal of the site at a Property Board meeting in March 2024. Initial work has been undertaken in terms of different options/layouts for the site (see also Council response to Matter 6).
W4 | Courtenay Road | 150 | Proposed allocation W4 | The site is controlled by Cala Homes, who commented on the Reg 19 LP supporting the site allocation, subject to suggested changes, and confirming its suitability and availability. The site is subject to phasing policy H2 and, while the site promoters want to develop earlier, the trajectory estimates completion in years 6-10 (2031/32 - 2034/35) (see also Council response to Matter 6). | Cala Homes (Southern) Supporting Vision Statement https://www.localplan.winchester.gov.uk/assets/inline/671/George-Whalley-OBO-CALA-Homes-W4-BHLF-AQTS-3263-7-vision-statement.pdf
H9 | Winchester student accommodation | 200 | This is not a site-specific allocation but a policy that enables the development of student accommodation in Winchester. The evidence for this is contained in the Student Accommodation Topic Paper. | The Student Accommodation Topic Paper includes evidence of future needs for and intentions to develop student accommodation for the Universities of Winchester and Southampton. As this is not a site-specific allocation the trajectory estimates delivery in the later part of the Plan period (2034/35 - 2037/38). There is a current planning application at Bushfield Camp which includes 525 student beds (210 dwelling equivalents). | see Student Accommodation Topic Paper
South Hampshire Urban Area
SH1 | Newlands (West of Waterlooville) | 300 | Allocated carried forward site SH2, with additional capacity of 300 dwellings proposed in Plan. | Grainger Site Delivery Statement shows various phases of the original allocation complete and others sold by Grainger to housebuilders and under construction. Grainger expect to deliver the additional capacity phases as follows: Phase 6A Extra Care delivery expected 2027 School extension land delivery expected 2030 Cemetery land delivery expected 2034 Phases M1 and M3 delivery expected 2029 The trajectory expects delivery of the additional dwellings in the later part of the Plan period (2033/34 - 2037/38). NOTE: the figure of 300 additional dwellings is in the submitted Local Plan - the Council is proposing a modification to increase this to 350 dwellings - (see also Council statement on Matter 7). | Bryony-Stala-obo-West-Waterlooville_Grainger-NON-AQTS-3B5G-A-Supporting-Document_Redacted.pdf
SH2 | North Whiteley | 200 | Allocated carried forward site SH3, with additional capacity of 200 dwellings proposed in Plan. | Development commenced, many phases of the original allocation completed or under construction. Several sites are proposed for the additional 200 dwellings, as set out in Council's statement on Matter 7. The main sites are owned by Crest Nicholson and Hampshire County Council, who have confirmed support for the site allocations and that the sites are available. The trajectory expects delivery of the additional dwellings in years 6-10 (2031/32 - 2034/35).
Market Towns and Rural Area
BW3 | Tollgate Sawmill | 10 | Brownfield site. Allocated mixed use site carried forward site BW5. | The previous agent confirmed deliverability in November 2023 (no longer acting for owner). It has not been possible to make contact with the site owner, the trajectory has been amended to estimate delivery of this site in years 6-10 (2031/32) (see also Council response to Matter 16).
BW4 | Land North of Rareridge Lane | 100 | Proposed allocation BW4 | The site's developer made representations on the submitted Local Plan, supporting the allocation and to confirm that the site is available and viable, and that they are willing to progress quickly to a planning application. Landscape mitigation strategy and access proposals received. The site is subject to phasing policy H2 and, while the site promoters want to develop earlier, the trajectory estimates delivery in years 6-10 (2031/32 - 2033/34) (see also Council response to Matter 8). | ANON-AQTS-3B54-Q
NA3 | New Alresford Neighbourhood Plan | 100 | Proposed allocation NA3. This is not a site-specific allocation but sets a target for housing provision in the New Alresford Neighbourhood Plan. | Neighbourhood Plan area designated 7 September 2021, community engagement undertaken 2021-23 together with preparation of evidence base. Community consultation undertaken November 2024, with consultation event on policies and alternative site allocations to deliver the quantum expressed in Policy NA3. Formal consultation (Regulation 14) proposed in Autumn 2025, prior to submission to WCC. Any site(s) are subject to phasing policy H2 and the trajectory estimates delivery of any allocated site(s) over the period 2031/32 - 2035/36 (see also Council response to Matter 8). | ANON-AQTS-32FT-R
CC1 | Clayfield Park | 48 | Brownfield site. Allocated carried forward site CC2. | Indicative phasing plan submitted in 2019 (with planning application) indicating 48 dwellings and retention of commercial building. This showed 4 phases of residential development between 2021 and 2028. Agent has confirmed a commitment to development (December 2024). Given delays to the original phasing, the trajectory has been amended to estimate delivery in years 6-10 (2030/31-2032/33) (see also Council statement in response to Matter 8).
CC2 | Colden Common Farm | 45 | Proposed allocation CC2 | The site is controlled by Forman Homes, who commented on the Reg 19 LP supporting the site allocation. The site is subject to phasing policy H2 and, while the site promoters want to develop earlier, the trajectory estimates completion in years 6-10 (2032/33 - 2033/34) (see also Council statement in response to Matter 8). | ANON-AQTS-32NP-V
CC3 | Land at Main Road | 35 | Proposed allocation | The site is controlled by Bargate Homes, who commented on the Reg 19 LP supporting the site allocation and confirming a commitment to delivery. The site is subject to phasing policy H2 and, while the site promoters want to develop earlier, the trajectory estimates completion in years 6-10 (2031/32 - 2032/33) (see also Council statement in response to Matter 8). | BHLF-AQTS-32Q8-7
CC4 | Land adjoining 85 Church Lane | 10 | Proposed allocation | Agent has confirmed a commitment to development (December 2024) and provided information regarding delivery and biodiversity net gain. The site is subject to phasing policy H2 and, while the site promoters want to develop earlier, the trajectory estimates completion in years 6-10 (2031/32 - 2032/33) (see also Council statement in response to Matter 8).
DEN1 | Denmead Neighbourhood Plan | 100 | Proposed allocation DEN1. This is not a site-specific allocation but sets a target for housing provision in the Denmead Neighbourhood Plan review. | Existing Neighbourhood Plan made on 1 April 2015. Review is in progress to extend the NP to 2039. Call for sites undertaken in 2023. Consultation on preferred sites October - November 2024, Site Assessment report published December 2024. Formal consultation (Regulation 14) proposed for May/June 2025. Any site(s) are subject to phasing policy H2 and the trajectory estimates delivery of any allocated site(s) over the period 2031/32 - 2035/36 (see also Council response to Matter 8). | Site selection paper which has identified the preferred sites for development.
KW2 | Land adjoining the Cart & Horses PH | 75 | Proposed allocation KW2. | The site promoter made representations on the submitted Local Plan which support the allocation of the site and refer to agreement in principle with HCC over access to the site. Although this site is not phased by policy H2, it is required to be accessed from an improved junction off the A33. Hence the trajectory estimates delivery of this site in years 6-10 (2030/31 - 2032/33) (see also Council response to Matter 8). | ANON-AQTS-32UM-Z
WK5 | Mill Lane | 40 | Proposed allocation WK5 | The site is controlled by Bloor Homes, who commented on the Reg 19 LP supporting the site allocation, subject to some suggested changes. The site is subject to phasing policy H2 and, while the site promoters want to develop earlier, the trajectory estimates completion in years 6-10 (2031/32 - 2032/33) (see also Council statement in response to Matter 8). | ANON-AQTS-329Q-8
WK6 | Land off Southwick Road | 60 | Proposed allocation WK6 | The site is controlled by Croudace Homes, who commented on the Reg 19 LP supporting the site allocation, subject to some suggested changes, and confirming its availability. Planning application 24/02803/FUL for 60 homes refused March 2025 on the basis that the site is greenfield and subject to a phasing policy to not come forward to 2030, rather than being refused on matters of detail. While the site promoters want to develop earlier, the trajectory estimates completion in years 6-10 (2031/32 - 2033/34) (see also Council statement in response to Matter 8). | BHLF-AQTS-328A-Q
HU1 | Hursley Neighbourhood Plan | 20 | Proposed allocation HU1. This is not a site-specific allocation and policy HU1 requires 20 dwellings either through windfall or the Hursley Neighbourhood Plan. The trajectory includes these 20 dwellings within the windfall allowance (and does not list HU1 separately). | Neighbourhood Plan area designated 15 January 2021. Site Assessment report agreed by PC and published in January 2025. According to the Parish Council, although at an early stage the Neighbourhood Plan is making progress with evidence gathering to be followed by draft proposals and a public consultation. The Parish Council anticipate the Neighbourhood Plan to be ‘made’ in 2026. Sites may also come forward as windfall in the interim. Any site(s) allocated will be subject to phasing policy H2 and the trajectory estimates delivery of any allocated site(s) over the period 2031/32 - 2035/36 (see also Council response to Matter 8). | Final-Site-Assessment-Report-for-Hursley-Parish-Council-2.pdf
OT01 | Land off Main Road | 55 | Proposed allocation OT1 | The site promoter made representations on the submitted Local Plan supporting the site allocation, subject to some suggested changes, and confirming its availability. The site is subject to phasing policy H2 and, while the site promoters want to develop earlier, the trajectory estimates completion in years 6-10 (2031/32 - 2032/33) (see also Council statement in response to Matter 8). | BHLF-AQTS-328Q-7
SWO1 | Land at West Hill Road North | 40 | Proposed allocation SW01 | The site is controlled by Beechcroft Developments, who made representations on the submitted Local Plan supporting the site allocation, subject to some suggested changes. The site is subject to phasing policy H2 and, while the site promoters want to develop earlier, the trajectory estimates completion in years 6-10 (2031/32 - 2032/33) (see also Council statement in response to Matter 8). | ANON-AQTS-32NH-M
SU01 | Land at Brightlands, Sutton Scotney | 60 | Proposed allocation SU01 | The site is controlled by Wates Developments, who commented on the Reg 19 LP supporting the site allocation, subject to some suggested changes. The site is subject to phasing policy H2 and, while the site promoters want to develop earlier, the trajectory estimates completion in years 6-10 (2031/32 - 2033/34) (see also Council statement in response to Matter 8). | BHLF-AQTS-3286-C