## Introduction
Matter 5: Site Allocations Methodology
Appendix 2
This Appendix contains information on the delivery of non-residential allocations in the Winchester Proposed Submission Plan.
The aim is for this appendix to provide information on the delivery of non residential allocations in the same way that Appendix 1 sets out information
for housing and mixed use allocations

## Delivery Information
Non-Residential Allocations Delivery Information
Local Plan Site Allocation Reference | Site name | Allocation | Planning Status as at 31st March 2025 | Delivery Information
Winchester Town
W5 | Bushfield Camp | 20 ha employment land | Partial Brownfield site. Allocated site WT3. Concept Masterplan approved 2023. Planning application submitted October 2023 | The city council has entered in a Planning Performance Agreement with the site promoter and a decision on the planning application is expected in June 2025. |  |  | ANON-AQTS-32U5-8
W10 | Former River Park Leisure Centre Site | Learning and non-residential uses | Cabinet agreed on the 9 March 2022 a five year period during which the University of Southampton must use reasonable endeavours to bring forward their proposal for a transformational development to the existing Winchester School of Art campus, working with local residents and partners to secure the best outcome for Winchester. | Ongoing discussions with the University of Southampton regarding meeting the requirements of the Cabinet Report.
W11 | University of Winchester / Royal Hampshire County Hospital | Academic, healthcare, student housing and residential | Unlike the other employment policies, Policy W11 is an enabling policy to facilitate academic and student housing and in this respect, there are no specific targets / quantities of development in this policy.
South Hampshire Urban Area
SH4 | Solent Business Park | 4ha employment land | Allocated site . Planning permission 19/00852/OUT for mixed use development including light industrial, day nursey, gym , hotel and restaurant/bar now lapsed. | Met site promoter in August 2023. Site promoter has confirmed avaiability and seeks greater flexibility regarding the range of uses for the site. | Supporting documents (comments on policies) | Supporting information (Employment Land matters) | Letter (covering letter)
SH6 | Botley Bypass | New Road | Allocated under Policy SHUA5 in LPP2. Planning permission 17/02023/HCS granted by HCC Nov 2017 | Funding approval for the Botley Bypass final phase was agreed by the County Council's Cabinet in July 2024. The bypass is expected to be completed in late Summer 2027. Initial vegetation clearance has commenced.
Market Towns and Rural Area
WK3 | Welborne Open Space | Open space | Allocated in adopted Local Plan Part 1 Policy SH4 | Outline planning application for Welborne approved in October 2019 and a revised application approved in 2021. No land within Winchester District is included.